## Scrum Details
Phase I
| Module | Features | Description | Priority | Duration | Start Date | End Date | Completed % | Percentage % | Resources
| Login feature | Location search - Near by Vendor | GPS System for Search for location
|  | Already member | Enter Login Email id / Password , if invaild email id enter system has to update the message.
|  | Sign up Screen | New User can register - with following filed information . 1) Name , Email id and password.
|  | Home Page display | Home Page display - with list of restaurant details.
|  | Filter option | Filter option to search restaurant details
|  | Forgot password | Email to enter to send the OTP password , if invaild email is enter , system has to update the message.
|  | Email sent | OTP screen to enter the OTP Number and vailadate the same.
|  | Choose your Password | Enter Password :- New Password / Confirm password , if both password are not matching system has to send the message alerts.
|  | Login screen | Once password is verified system has to re- direct to login screen.
Phase II | Select Restaurant | Select the Restaurant details | Select the Indivdual restaurant details for the list available , system has to display the food category & food item list
|  | Individual Item details | select the individual item details , option to add up qty details & add to card functionality .
|  | Home page with add to card icon | Selected restaurant home page screen update with add to cart icon , shoiwng how any item are selected and added to cart icon.
|  | Add to Cart | Allow to add multiple item , process to check out. With special instruction added.
|  | Order Summary | View Order summary before making a Payment.
|  | Payment Gateway | Payment will be made through payment gateway stripe.
|  | order history & Track | Order History page with order status details & Track
|  | Add Card & Edit card | Add Card & Edit card , system has to vailadate the card number and vendor details . If inavaild system has to display the invaild message.
Phase III | Notification & Menu Page | Notification on order accepted / rejected | Home page should received notification on accepted or rejected the order .
|  | Order Completed | Notification on order completed
|  | Profile Menu | Profile Menu with edit feature.
|  | Reset Password fetaure | Reset Password feature.
Phase IV | Restaurant App login feature | Location search - Near by Vendor | GPS System for Search for location
|  | Already member | Enter Login Email id / Password , if invaild email id enter system has to update the message.
|  | Sign up Screen - RESTAURANT DETAILS | following data for Restaurant details like :- Restaurant Name, Password, Restaurant type, Address, Time detais .
|  | Home Page display - My dish | Food Category with sub category Food Item .
|  | Add Dish | Add dish food category / Food Item base on Data create from web pannel.
|  | Dish Details | Dish details added the same .
|  | Current Order | Current order details / With option for accepted or rejected / order ready for Collection
|  | Notification | Base on the Current order option system will send the notification to the student app.
Phase V | Order Details
|  | Order Details | click on the indivdual order to view Order details
|  | Order History | order history with filter date and its status , delivered or pending.
|  | Rating & Review | Rating & Review submit by the stundent for individual restaurant.
|  | Profile | Profile Editing & Time details.
Phase V | Web Site Admin Panel
|  | User Listing / view invidual user order. | User Listing - Using app also order details placed by them
|  | Item Creation and Listing | item creation / item category wise
|  | Order Tracking Distance & Pick Up Details | Order Tracking - Pick up & delivery point.
|  | Status Option - Rejected / Approve Order Base on Location Pick up. | Vendor Authorized to approve / rejected order placed
|  | History order details | History Order details
|  | Notification Management / Distance details | Manage Notification , Distance management - update the distance details KM/ Mile for order pick up .

## Sprint Details
1
Sprint 1 Work Log Items (02-Jan-2017 to 13-Jan-2017)
|  | Baseline | Actual/Forecast | Remarks
Item | Scheduled Item Description | Date | Date
Web Application – Admin Panel
1 |  | 2017-01-03 | 2017-01-04
|  | 2017-01-05 | 2017-01-06
2
3 |  | 2017-01-09 | 2017-01-09
4 |  | 2017-01-11 | 2017-01-11
Admin Portal API
1 |  | 2017-01-02 | 2017-01-02
|  | 2017-01-03 | 2017-01-03
2
|  | 2017-01-04 | 2017-01-04
3
|  | 2017-01-05 | 2017-01-06
4
5 |  | 2017-01-09 | 2017-01-09
6 |  | 2017-01-10 | 2017-01-10
7 |  | 2017-01-11 | 2017-01-11
Other Tasks
1 | UAT environment setup
2 | iPad - Setup Details
3 | Email Format
4 | Order Item Listing

## Web application
S.no | Feature listing Of Web Application
1 | Admin User Login
2 | Create account
3 | Forgot Password
4 | Change password
5 | User Listing / view invidual user order.
6 | Item Creation and Listing
7 | Order Tracking Distance & Pick Up Details
8 | Status Option - Rejected / Approve Order Base on Location Pick up.
9 | History Invoice details
10 | Notification Management

## Mobile Application
S.no | Mobile Application
1 | Student Registeration / Already Register Student
2 | Create Account
3 | Forgetpassword
4 | Change Password
5 | Menu List
6 | Profile View
7 | Selection of Carteen
8 | Order Item
9 | Add To Cart
10 | Pickup Time and Location details
11 | Payment Details
12 | Order Listing Or Invoice with Pick up time